## Timeline
Screens | Front-End UI Expected Time(hrs) | Front-End API Linking Expected Time(hrs) | Back-End API Expected Time(hrs)
Welcome page | 1 | 1
Login | 2 | 2
Register | 3 | 3
Dashboard | 1 | 1
Setup
Numbering | 1
Game Setup
Play
Select Game
Game screen
Verify
Bingo 90 Tickets
Approve Users
Reports
Game details
Help | 0.5 | 0.5
Feedback | 1 | 1

## FE task status
Date | Task Type | From | To | Total Hours Spent | Task Detail | Notes | Status
2021-07-29 | Designing | 14:30 | 16:30 | 2:00 | User List | Link creation, window, table design and display | Completed
2021-07-29 | Development | 16:30 | 17:30 | 1:00 | API implementation - Registration | Api implimentation with front end validation | Completed
2021-07-29 | Development | 13:00 | 14:30 | 1:30 | API implementation - Login/Logout | Api implimentation with front end validation | Completed
2021-07-27 | Designing | 16:00 | 16:45 | 0:45 | Ticket verify display | adding css , row highlighting while verification | Completed
2021-07-27 | Development | 16:45 | 17:30 | 0:45 | API implementation - Ticket verification | ticket verrification Api implimentation | Completed
2021-07-27 | Development | 14:00 | 16:00 | 2:00 | Play - Select Game | Adding validations to the inputboxes | In-Progress
2021-07-27 | Designing | 11:00 | 14:00 | 3:00 | Play - Select Game | Designing the window for Select Game | Completed
2021-07-27 | Designing | 9:30 | 11:00 | 1:30 | Verify - Bingo 90 Tickets | Designing the window for Bingo tickets also doing validations | Completed
2021-07-26 | Development | 9:30 | 17:30 | 8:00 | API implementation | Implementing API call for getMasterColors, Numbers Also rectified some issues with API setup and CORS issues. | Completed
2021-07-24 | Development | 9:30 | 16:15 | 6:45 | Play - Game Screen->Start,Pause,Audio On/OFF,Dictate | Coding the logic for Auto number calls. Displaying number in various sections. Coding the logic for pause and re-start. Adding voice to number called. | Completed
2021-07-23 | Development | 16:30 | 17:30 | 1:00 | Play - Game Screen->Start | Coding the logic for Auto number calls. Displaying number in various sections. | In-Progress
2021-07-23 | Designing | 9:00 | 16:30 | 7:30 | Play - Game Screen | Designing & structuring | In-Progress
2021-07-22 | Development | 9:00 | 17:00 | 8:00 | Game Setup - New Setup | Completed the UI and dynamic interaction of the flow with javascript code(only used the static json data). DB and API not yet used | Completed
2021-07-21 | Designing | 16:30 | 17:31 | 1:01 | Game Setup | Working on Game setup UI structure | In-Progress
2021-07-21 | Designing | 15:00 | 16:30 | 1:30 | Numbering | UI completed | Completed
2021-07-21 | Designing | 15:00 | 16:15 | 1:15 | Dashboard | UI completed | Completed
2021-07-21 | Designing | 14:00 | 15:00 | 1:00 | Register | UI completed and linked to the link | Completed
2021-07-21 | Designing | 13:30 | 14:00 | 0:30 | Login | UI completed and linked to the link | Completed
2021-07-21 | Designing | 12:30 | 13:30 | 1:00 | Welcome page | UI completed | Completed

## Sheet2
Development | Completed
Designing | Learnt
RND | Kept Pending
Learning | In-Progress
Other